## CCR Testcases
|  |  |  | Date | 2022-11-15
|  |  |  | Team ID | PNT2022TMID45523
|  |  |  | Project Name | Project - Customer Care Registry
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Commenets | TC for Automation(Y/N) | BUG ID | Executed By
1 | Functional | Registration Page | Customer is trying to register with the invalid data |  | 1. Go to application 2. Click "Don’t have an account? Register" 3. Enter first name, last name, select the role, password and confirm password 4. Click Register button | First Name = vasanth Last Name = kaviya Role = Customer Email = suryaskaviya10@gmail.com Password = 11111111 Confirm Password = 1111111 | Customer should get an alert saying “Passwords do not match” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
2 | Functional | Registration Page | Customer is trying to register with the invalid data |  | 1. Go to application 2. Click "Don’t have an account? Register" 3. Enter first name, last name, select the role, password and confirm password 4. Click Register button |  | Customer should get an alert saying “Invalid email” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
3 | Functional | Registration Page | Customer is trying to register with the invalid data |  | 1. Go to application 2. Click "Don’t have an account? Register" 3. Enter first name, last name, select the role, password and confirm password 4. Click Register button |  | Customer should get an alert saying “Firstname should be atleast 6 characters long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
4 | Functional | Login page | Customer is trying to register with the invalid data |  | 1. Go to application 2. Click "Don’t have an account? Register" 3. Enter first name, last name, select the role, password and confirm password 4. Click Register button | First Name = Bala Last Name = Abinesh Role = Customer Email = suryathaya10@gmail.com Password = 1234 Confirm Password = 1234 | Customer should get an alert saying “Passwords must be at least 8 characters long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
5 | Functional | Registration Page | Customer is trying to register with the valid data |  | 1. Go to application 2. Click "Don’t have an account? Register" 3. Enter first name, last name, select the role, password and confirm password 4. Click Register button | First Name = karthi Last Name = Abinesh Role = Customer Email = karthi001@gmail.com Password = 12345678 Confirm Password = 12345678 | Customer's profile is added in the database and the customer is registered. Then, the customer is re-directed to the Login page to login | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
6 | Functional | Login Page | Customer is trying to login using the invalid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = karthi001gmail.com Password = 00000000 | Customer should get an alert saying “Invalid email” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
7 | Functional | Login Page | Customer is trying to login using the invalid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email=vicky311@gmail.com | Customer should get an alert saying “User does not exist” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
8 | Functional | Login Page | Customer is trying to login using the invalid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = suryathaya10@gmail.com Password = 12345678999 | Customer should get an alert saying “Wrong Password!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
9 | Functional | Login Page | Customer is trying to login using the valid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = jokerkiruba133@gmail.com Password = 10796686 | Customer should login to the application. The customer should see the dashboard | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
10 | Functional | Login Page | Admin is trying to login using the invalid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = joker.ccr@gmail.com Password = 001 | Admin should get an alert saying ‘Invalid Password!’ | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
11 | Functional | Login Page | Admin is trying to login using the invalid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = vasanth@gmail.com Password = kaviya2022 | Admin should get an alert saying ‘Invalid Email!’ | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
12 | Functional | Login Page | Admin is trying to login using the valid credentials |  | 1. Go to application 2. Enter email, password 3. Click Login | Email = kaviya@gmail.com Password = kaviya.ccr@2022 | Admin should login to the application. Admin should be able to see the dashboard | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
13 | Functional | Customer dashboard | Customer is trying to log out | **Customer already logged in** | 1. Go to Nav Bar and click "Cart icon" 2. Click the "LOGOUT" button | NULL | Customer should be able to log out from the application | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
14 | Functional | Admin dashboard | Admin is trying to log out | **Admin already logged in** | 1. Go to Nav Bar and click "Admin icon" 2. Click the "LOGOUT" button | NULL | Admin should be able to log out from the application | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
15 | Functional | New ticket section in the Customer dashboard | Customer creating a new ticket with empty query | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “New Ticket” option in the Dashboard 4. Clicking the “New Ticket” button without typing any query in the given text area | Query = NULL | Customer should get an alert saying “Query cannot be empty!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
16 | Functional | New ticket section in the Customer dashboard | Customer creating a new ticket with valid query | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “New Ticket” option in the Dashboard 4. Typing the query in the given text area 5. Clicking the “New Ticket” button | Query = “Hi. My I Phone 14 pro max is not turning on. It is a new unit I bought it just 2 days back. I don’t know what happened. Can you help me please?” | The ticket gets inserted in the database. After that customer gets an alert saying ‘Ticket created’ | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
17 | Functional | Tickets section in the Customer dashboard | Customer seeing all the tickets raised by him/her | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “Tickets” option in the Dashboard | Tickets created by the customer which are already being inserted in the database | Customer should see the list of all the tickets raised by him/her | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
18 | Functional | Tickets section in the Customer dashboard | Customer seeing all the tickets raised by him/her | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “Tickets” option in the Dashboard | ** No tickets ** | Customer should see a message “You are yet to raise a ticket” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
19 | Functional | Tickets section in the Customer dashboard | Customer seeing the query of a ticket | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “Tickets” option in the Dashboard 4. Click “View” option in a ticket from the list of tickets | Tickets created by the customer which are already being inserted in the database | An alert should be shown having the actual query posted by the customer | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
20 | Functional | Tickets section in the Customer dashboard | Customer seeing the assigned agent for a ticket | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “Tickets” option in the Dashboard | • Tickets created by the customer which are already being inserted in the database • Admin assigned the agent for the ticket | Customer should be able to see the first name of the agent assigned | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
21 | Functional | Tickets section in the Customer dashboard | Customer seeing the assigned agent for a ticket | **Customer already logged in** | 1. Go to site 2. Customer login using email and password 3. Click “Tickets” option in the Dashboard | • Tickets created by the customer which are already being inserted in the database • Admin is yet to assign the agent | Customer should be able to see the “N/A” message displayed | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
22 | Functional | Unassigned tickets section in the Admin dashboard | Admin seeing all the unassigned tickets | **Admin already logged in** | 1. Click “Unassigned Tickets” option in the Dashboard | • Tickets created by the customers which are already being inserted in the database • Admin did not assign agent for the tickets | Showing the tickets that are yet to be assigned an agent by the admin | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
23 | Functional | Unassigned tickets section in the Admin dashboard | Admin seeing all the unassigned tickets | **Admin already logged in** | 1. Click “Unassigned Tickets” option in the Dashboard | • Tickets created by the customers which are already being inserted in the database • Admin assigned agents for all the tickets | Admin should just see the message “There is nothing left to assign” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
24 | Functional | Unassigned tickets section in the Admin dashboard | Admin assigning an agent for a ticket | **Admin already logged in** | 1. Click “Unassigned Tickets” option in the Dashboard | • Tickets created by the customers which are already being inserted in the database • Admin did not assign the agent yet | Admin should get an alert saying “Do you really want to assign the agent for this ticket?”. If admin clicks OK, then the agent is assigned for the ticket. The list gets updated | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
25 | Functional | Requests section in the Admin dashboard | Admin seeing the requests section | **Admin already logged in** | 1. Click “Requests” option in the Dashboard | • Agent details in the database • Admin is yet to accept the agent | Admin should be able to see the list of all the requests made by the agents to the admin | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
26 | Functional | Requests section in the Admin dashboard | Admin seeing the requests section | **Admin already logged in** | 1. Click “Requests” option in the Dashboard | • Agent details in the database • Admin accepted all the agents | Admin should just see the message “There are no pending requests” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
27 | Functional | Requests section in the Admin dashboard | Admin accepting an agent from the request section | **Admin already logged in** | 1. Click “Requests” option in the Dashboard 2. Click “Tick” mark that is against the agent details | • Agent details in the database • Admin is yet to accept the agent | The agent gets accepted and the same is updated in the database. The list gets updated | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
28 | Functional | Reistration Page | Agent registration using invalid data |  | 1. Go to site 2. Click on “Don’t have an account yet? Register” option 3. Fill the form | First Name = Agent 1 Last Name = NULL Email = agent1@gmail.com Password = 12345678 Confirm password = 12345678 | Agent should get an alert saying “Last Name must be at least 1 character long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
29 | Functional | Reistration Page | Agent registration using invalid data |  | 1. Go to site 2. Click on “Don’t have an account yet? Register” option 3. Fill the form | First Name = Agent 1 Last Name = Agent Email = agent1gmail.com Password = 12345678 Confirm password = 12345678 | Agent should get an alert saying “Invalid Email” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
30 | Functional | Reistration Page | Agent registration using invalid data |  | 1. Go to site 2. Click on “Don’t have an account yet? Register” option 3. Fill the form | First Name = Agent 1 Last Name = Agent Email = agent1@gmail.com Password = 123456789 Confirm password = 12345678 | Agent should get an alert saying “Passwords do not match!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
31 | Functional | Reistration Page | Agent registration using invalid data |  | 1. Go to site 2. Click on “Don’t have an account yet? Register” option 3. Fill the form | First Name = Agent 1 Last Name = Agent Email = agent1@gmail.com Password = 1234 Confirm password = 1234 | Agent should get an alert saying “Passwords must be at least 8 characters long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
32 | Functional | Reistration Page | Agent registration using the valid data |  | 1. Go to site 2. Click on “Don’t have an account yet? Register” option 3. Fill the form | First Name = Agent 1 Last Name = Agent Email = agent1@gmail.com Password = 12345678 Confirm password = 12345678 | Agent details gets updated in the database. Then an alert “Account created. Login!” is shown | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
33 | Functional | Login Page | Agent login using the invalid data |  | 1. Go to site 2. Fill out the login form 3. Enter email and password | Email = agent1@gmail Password = 12345678 | Agent should get an alert “Invalid email” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
34 | Functional | Login Page | Agent login using the invalid data |  | 1. Go to site 2. Fill out the login form 3. Enter email and password | Email = agent1@gmail Password = 12345678 | Agent should get an alert “Invalid email” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
35 | Functional | Login Page | Agent login using the invalid data |  | 1. Go to site 2. Fill out the login form 3. Enter email and password | Email = agent@gmail.com Password = 12345678 | Agent should get an alert “Agent does not exist!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
36 | Functional | Login Page | Agent login using the valid data |  | 1. Go to site 2. Fill out the login form 3. Enter email and password | • Email = agent1@gmail.com Password = 12345678 • Admin did not accept the agent yet | Agent should be redirected to a page, that has the status of the confirmation | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
37 | Functional | Login Page | Agent login using the valid data |  | 1. Go to site 2. Fill out the login form 3. Enter email and password | • Email = agent1@gmail.com Password = 12345678 • Admin accepted the agent yet | Agent should be able to login to the site. Agent should see the dashboard | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
38 | Functional | Password section in the Customer dashboard | Customer changing the existing password using invalid data | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Change Password” in the dashboard | Password = 123456 New Password = 123456789 Confirm Password = 123456789 | Customer should get an alert saying “Passwords must be at least 8 characters long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
39 | Functional | Password section in the Customer dashboard | Customer changing the existing password using invalid data | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345678 New Password = 123456789 Confirm Password = 123456780 | Customer should get an alert saying “Passwords do not match!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
40 | Functional | Password section in the Customer dashboard | Customer changing the existing password using invalid data | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345678 New Password = 12345678 Confirm Password = 12345678 | Customer should get an alert saying “Old and New password cannot be the same!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
41 | Functional | Password section in the Customer dashboard | Customer changing the existing password | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345678 New Password = 123456789 Confirm Password = 123456789 | Customer should get an alert saying “Password changed! Please Login”. The customer is then redirected to the login page for logging in | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
42 | Functional | Tickets section in the Customer dashboard | Customer opening the address column | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat/Visit” in the address column of a ticket | Tickets in the database | Customer should be able to get into the address column, where the latter can chat with the agent | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
43 | Functional | Address column section in the Customer dashboard | Customer opening the address column | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat” in the address column of a ticket | • Ticket in the database • Ticket is still OPEN • Still, no messages with the agent • Agent first name = ‘Agent 1’ | Customer should see an alert saying “Start the conversation with the Agent 1” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
44 | Functional | Address column section in the Customer dashboard | Customer opening the address column | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat” in the address column of a ticket | • Ticket in the database • Ticket is still OPEN • Previous messages b/w the agent and customer • Agent first name = ‘Agent 1’ | Customer should see all the messages b/w the customer and agent | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
45 | Functional | Address column section in the Customer dashboard | Customer opening the address column | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat” in the address column of a ticket | • Ticket in the database • Ticket is CLOSED • Previous messages b/w the agent and customer • Agent first name = ‘Agent 1’ | Customer should see all the messages b/w the customer and agent. At the bottom, a red alert saying “You closed the ticket. Chat is disabled” is shown | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
46 | Functional | Address column section in the Customer dashboard | Customer sending a message in the address column | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket 5. Type the message and click send button / hit enter | • Ticket in the database • Ticket is OPEN • Message = “Can you please help me?” | Customer’s message is inserted in the database and the chats are reloaded | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
47 | Functional | Address column section in the Customer dashboard | Customer sending a message in the address column with an empty message | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket 5. Click send button / hit enter | • Ticket in the database • Ticket is OPEN • Message = “” | Customer should get an alert saying “Please fill out this field” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
48 | Functional | Change password section in the Agent dashboard | Agent changing the password with the invalid data | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345676 New Password = 123456789 Confirm Password = 123456789 | Agent should get an alert saying “Passwords must be at least 8 characters long!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
49 | Functional | Change password section in the Agent dashboard | Agent changing the password with the invalid data | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Change Password” in the dashboard | Password = 313312423 New Password = 111121212 Confirm Password = 12342522 | Agent should get an alert saying “Passwords do not match!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
50 | Functional | Change password section in the Agent dashboard | Agent changing the password with the invalid data | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345678 New Password = 12345678 Confirm Password = 12345678 | Agent should get an alert saying “Old and New password cannot be the same!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
51 | Functional | Change password section in the Agent dashboard | Agent changing the password | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Change Password” in the dashboard | Password = 12345678 New Password = 123456789 Confirm Password = 123456789 | Agent should get an alert saying “Password changed! Please Login”. The customer is then redirected to the login page for logging in | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
52 | Functional | Address column section in the Agent dashboard | Agent opening the address column | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat/Visit” in the address column of a ticket | Tickets in the database | Agent should be able to get into the address column, where the latter can chat with the customer | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
53 | Functional | Address column section in the Agent dashboard | Agent opening the address column | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat” in the address column of a ticket | • Ticket in the database • Ticket is still OPEN • Still, no messages with the customer • Customer first name = ‘Bala’ | Agent should see an alert saying “Start the conversation with the Bala” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
54 | Functional | Address column section in the Agent dashboard | Agent opening the address column | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Chat” in the address column of a ticket | • Ticket in the database • Ticket is still OPEN • Previous messages b/w the agent and customer • Customer first name = ‘Bala’ | Agent should see all the messages b/w the customer and agent | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
55 | Functional | Address column section in the Agent dashboard | Agent opening the address column | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket | • Ticket in the database • Ticket is CLOSED • Previous messages b/w the agent and customer • Customer first name = ‘Bala’ | Agent should see all the messages b/w the customer and agent. At the bottom, a red alert saying “Bala closed the ticket. Chat is disabled” is shown | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
56 | Functional | Address column section in the Agent dashboard | Agent sending a message in the address column | ** Agent already logged in ** | 1. Go to site 2. Login as an agent using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket 5. Type the message and click send button / hit enter | • Ticket in the database • Ticket is OPEN • Message = “Yes, I can help you!” | Agent’s message is inserted in the database and the chats are reloaded | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
57 | Functional | Address column section in the Agent dashboard | Agent sending a message in the address column | ** Agent already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket 5. Click send button / hit enter | • Ticket in the database • Ticket is OPEN • Message = “” | Agent should get an alert saying “Please fill out this field” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
58 | Functional | Address column section in the Customer dashboard | Customer closing a ticket | ** Customer already logged in ** | 1. Go to site 2. Login as a customer using valid credentials 3. Click “Tickets” in the dashboard 4. Click “Visit” in the address column of a ticket 5. Click “CLOSE TICKET” in the Nav Bar | • Tickets in the database • Ticket is still OPEN | Status of the ticket is set to CLOSED in the database and the customer is redirected to all tickets page | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
59 | Functional | Forgot Password Page | Customer forgot the password and trying to update the password with invalid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email =suryaskaviya@gmail.com Role="Customer" | Customer should get an alert saying “Invalid email!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
60 | Functional | Forgot Password Page | Customer forgot the password and trying to update the password with invalid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email = vasanth001@gmail.com Role = “Customer” | Customer should get an alert saying “Customer does not exist” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
61 | Functional | Forgot Password Page | Customer forgot the password and trying to update the password with the valid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email = suryathaya10@gmail.com Role = “Customer” | Customer should receive an 8-digit code in the email and redirected to the code entering page | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
62 | Functional | Forgot Password Page | Customer entering invalid code to change the password | 1. Customer entered a valid email 2. Customer got the code In the email | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter invalid code 6. Click “Submit” button | Email = vasanth899@gmail.com Role = “Customer” Code = “bhuudbuuygdy2” | Customer should get an alert saying "Invalid code!" | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
63 | Functional | Forgot Password Page | Customer entering valid code to change the password | 1. Customer entered a valid email 2. Customer got the code In the email | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button | Email = suryaskaviya@gmail.com Role = “Customer” Code = “8743861” | Customer should be redirected to the passwords entering page | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
64 | Functional | Forgot Password Page | Customer entering the invalid passwords in the change password page | 1. Customer entered a valid email 2. Customer got the code In the email 3. Customer entered the valid code | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button 7. Enter the passwords | Password = 12345678 Confirm password = 87654321 | Customer should get an alert saying “Passwords do not match!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
65 | Functional | Forgot Password Page | Customer entering the new passwords in the change password page | 1. Customer entered a valid email 2. Customer got the code In the email 3. Customer entered the valid code | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button 7. Enter the passwords | Password = 12345678 Confirm password = 12345678 | Customer’s password gets updated. Then the customer is redirected to the login page to login | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
66 | Functional | Forgot Password Page | Agent forgot the password and trying to update the password with invalid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email = jokergmail.com Role = “customer” | Agent should get an alert saying “Invalid email!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
67 | Functional | Forgot Password Page | Agent forgot the password and trying to update the password with invalid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email = agent44gmail.com Role = “Agent” | Agent should get an alert saying “Agent does not exist” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
68 | Functional | Forgot Password Page | Agent forgot the password and trying to update the password with the valid email |  | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button | Email = agent1@gmail.com Role = “Agent” | Agent should receive an 8-digit code in the email and redirected to the code entering page | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
69 | Functional | Forgot Password Page | Agent entering invalid code to change the password | 1. Agent entered the valid email | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter invalid code 6. Click “Submit” button | Code = “bhuudbsgygdy2” | Agent should get an alert saying "Invalid code!" | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
70 | Functional | Forgot Password Page | Agent entering the valid code to change the password | 1. Agent entered the valid email | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button | Code = “87436601” | Agent should be redirected to the passwords entering page | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
71 | Functional | Forgot Password Page | Agent entering the invalid passwords in the change password page | 1. Agent entered the valid email 2. Agent got the code in the email 3. Agent entered the valid code | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button 7. Enter the passwords | Password = 12345678 Confirm password = 87654321 | Agent should get an alert saying “Passwords do not match!” | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.
72 | Functional | Forgot Password Page | Agent entering the new passwords in the change password page | 1. Agent entered the valid email 2. Agent got the code in the email 3. Agent entered the valid code | 1. Go to the site 2. Click “Forgot Password?” option in the Login form 3. Enter the email 4. Click “Get Code” button 5. Enter the valid code received in the email 6. Click “Submit” button 7. Enter the passwords | Password = 12345678 Confirm password = 12345678 | Agent’s password gets updated. Then the customer is redirected to the login page to login | Working as expected | Pass | Everything is working properly |  |  | kamalasree, kanimozhi, kaviya, kirubanithi.

## Test Scearnios
| Test Scenarios | User Type
1 | Verifying customer is able to login to the application | Customer
2 | Verifying customer is able to logout of the application | Customer
3 | Verifying customer is able to change the password | Customer
4 | Verifying customer is able to create a new ticket | Customer
5 | Verifying customer is able to see all the tickets created | Customer
6 | Verifying customer is able to have a chat with the Agent | Customer
7 | Verifying customer is able to close the ticket | Customer
8 | Verifying customer is able to see the past chats with the agents | Customer
9 | Verifying customer is able to change the password using the Forgot password option | Customer
10 | Verifying customer is able to receive all the necessary mails | Customer
1 | Verifying agent is able to login to the application | Agent
2 | Verifying agent is able to logout of the application | Agent
3 | Verifying agent is able to change the password | Agent
4 | Verifying agent is able to create a new ticket | Agent
5 | Verifying agent is able to see all the tickets created | Agent
6 | Verifying agent is able to have a chat with the Agent | Agent
7 | Verifying agent is able to close the ticket | Agent
8 | Verifying agent is able to see the past chats with the agents | Agent
9 | Verifying agent is able to change the password using the Forgot password option | Agent
10 | Verifying agent is able to receive all the necessary mails | Agent
1 | Veriying admin is able to login to the appication | Admin
2 | Veriying admin is able to logout of the application | Admin
3 | Verifying admin is able to see all the requests by the agents | Admin
4 | Verifying admin is able to see all the unassigned tickets | Admin
5 | Verifying admin is able to asssign an agent for a ticket | Admin
6 | Verifying admin is able to see all the feedbacks submitted | Admin